Notes 1st Steering Group Meeting ‘I am Roma’ Brussels

Date:		May 30/31, 2011

Place:		Brussels, QeC office

Present:	Heraklion Municipality (EL): Drousou Zacharia and Mavromati Adamantia

Belfast Health and Social Care Trust (UK): Alexandra McCarry and Lindsay Anderson

QeC-ERAN (BE): Haroon Saad, Giukia Cantaluppi, Caterina Torchiaro

and Managing Authority for the ESF in Lazio Region (IT)

Programme

- Overview project ‘I am Roma’

- Presentation of the partners

- Management and administration of the project

- Action Plan

Ad 1. Overview project ‘I am Roma’

Haroon Saad explained the role of LUDEN (aka QeC-ERAN) and gave an overview of what has been agreed regarding the project ‘I am Roma’. There were no specific questions/discussions.

Ad 2. Presentation of the partners

All partners presented their organizations and the challenges they face regarding to Roma.              The remarks and questions provided input for the capacity building workshop (discussed in Ad 4).        All presentations will be available through the website.

Ad 3. Management and administration of the project

- Finance: Haroon Saad explained the different forms to be used in the project. First thing to do back home is to prepare the staff declaration forms. Partners are required to collect proof: every payment and activities that happened need to be documented, there is no space for errors!             A suggestion is that forms are first send by email for a check to GIULIA CANTALUPPI

- Reports: The reports can be made in the local language. It is good to remember that every activity has to be evaluated.

- Website: http://iamroma.qec-eran.org/

Ad 4. Action Plan

- Phase 1: 0-6 months

  - 1st SGM

  - Project website with the management platform

  - Planning for the capacity building workshop

  - Establish LAG´s. It is important to have the different roles (activists, knowledge persons and communicators) are represented in the LAG´s. The profiles will be checked on this. LUDEN will design templates for the profiles.

- Phase 2: 6-12 months

  - 1st transnational workshop: Capacity building

  - 2nd SGM (combined with workshop)

  - Local Capacity building workshops

  - Online exchange programme

  - Good practice (Capacity building compendium)

  - Development of local campaign

- Phase 3: 12-20 months

  - 2nd transnational workshop

  - 3rd SMG (combined with workshop)

  - Local campaigns undertaken

  - Online events

  - Local campaign materials (good practices, data base)

- Phase 4: 20-24 months

  - 4th SGM (last)

  - Transnational dissemination event

  - Local dissemination events

  - Final report(s)

Detailed planning for the next 6 months:

|  | Item | Who | Deadline |
| --- | --- | --- | --- |
| 1 | Staff declaration form send to LUDEN (date 1 of February) | Partners | End of June |
| 2 | Timesheet for 2 month (feb/march) (april:may) | Partners | End of June |
| 3 | Proof of Payment | Partners | End of June |
| 4 | Expenses claim | Partners | 10 June |
| 5 | Website guide send to partners | LUDEN | End of June |
| 6 | Accounts created on the website | Local coordinators | Now |
| 7 | LAG Profile template send to local coordinators LAG profiles on platform | LUDEN Partners | June 30 |
| 8 | Details of participants to Capacity building workshop and 2nd SGM send to LUDEN | Local coordinators | July 15 |
| 9 | Capacity building workshop and 2nd SGM | Local coordinators + 3 participants per partner | Sept 26-29 |

Ad 5. Initial ideas for the capacity building workshop

The capacity building workshop will be held in Sintra, form September 26 to 29. In the budget there is room for translation in three languages. When the participants are known a decision will be made on the third language, as English and Portuguese needs to be in the list.

During the presentations some elements were mentioned:

- Legal: EU context (children and human rights, antidiscrimination), Case Law (e.g. school segregation and redefining cases in such a way that it is not seen as discrimination). Some partners would also like to see a spin off regarding raising awareness of rights targeted at Roma.

- Profile of Roma discrimination: stereotypes, gender, age, etc.

- Good practices: E.g. human rights & local monitors network, family planning & health communication. There is also a wish to include a field visit in the programme.

- Resources: Sharing resources that can be used during the local capacity building workshops.