ACTION PLAN

| Month | Action | WHO/WHERE | MILESTONES |
| --- | --- | --- | --- |
| 4/5 February | Steering Group Meeting 1 | Brussels All partners |  |
| End February | STAFF Declaration form And contract | All partners To QeC |  |
| End February | Expensive claim 1sgm | Partners All To QeC |  |
| End of March End of March 14 of May Before of April First week of May | 1.Establish Local Action Groups (MINIMUM 6) 2.Profiles of LAG members 3.Local Mapping 4. Hold first meeting LAG 5. Select Participants for first PREW | All partners Partner + 3 local members | Format for every LOCAL member + photo In your own languages In English |
| End of February | Online Portal-central framework(draft version) For news contact local news paper: - RSS from all partners - 2 key words in your languages | All partners |  |
|  | Feedback from partners | All partners | Contact Nicolas |
| End of March | Online portal final version | QeC-ERAN |  |
| April | Test Online Conference | All partners | Email for communication + link |
|  | Conduct Local Mapping and Forum In relation to the agreed themes | All Partners |  |
| 9/11 June | Trans national Peer Review 1 |  | 1.Lyon(10 February) 2. Athens |
|  | Steering Group Meeting 2 |  |  |
|  | Meeting 2 LAGs-feedback Select participants for second PREW | All partners |  |
|  | TPRW 1 Report | External expert |  |
|  | Project Interim Report | Qec + all partners |  |
|  | Transnational Peer Review 2 |  |  |
|  | Steering Group Meeting 3 |  |  |